## Generic Checklist
Generic Technical Readiness Assessment (TRA) Checklist
Phase | Category | Action Item (Task) | Role / Owner | Reference Source (As-Is from TRA Article) | Status
PLANNING (BURP) | Setup | Create 'Technical Readiness Assessment' page in Confluence | Tech Lead | Create the Technical Readiness Assessment for all new Type 1 Features... stored in Confluence. | ⬜ Pending
PLANNING (BURP) | Scoring | Assign Initial 'Technical Risk' and 'Mitigation Risk' Scores | Architect | Assign an initial technical risk score to the anticipated approach. | ⬜ Pending
PLANNING (BURP) | Gate | VAT Lightning Review (Mandatory if any Score is HIGH) | Zone Architect | Any Feature with a high technical risk score will require a VAT lightning review. | ⬜ Pending
PLANNING (BURP) | Gate | Core Team Review (Mandatory if any Score is MEDIUM) | Tech Lead | Scores set to Medium... expect those features to be reviewed by the core technical and product team. | ⬜ Pending
ALPHA | Assessment | Complete TRA Sections/Questions for Alpha Phase | Tech Lead | Prior to each rollout phase (Alpha, Beta, GA), complete the associated TRA sections. | ⬜ Pending
ALPHA | Scoring | Update Risk Scores (if scope/risk changed) | Architect | Enter Technical and Mitigation Risk Scores... Based on the responses within the Assessments. | ⬜ Pending
ALPHA | Gate | VAT/Core Review (Required if Scores increased to Med/High) | Zone Architect | If the Feature has a High Technical Risk score... an additional VAT review is required. | ⬜ Pending
ALPHA | Signoff | Jira Feature: Engineering Signoff for Alpha | Eng Lead | A signoff from each of Product and Engineering are required for each phase of release. | ⬜ Pending
ALPHA | Signoff | Jira Feature: Product Signoff for Alpha | Product Owner | A signoff from each of Product and Engineering are required for each phase of release. | ⬜ Pending
BETA | Assessment | Complete TRA Sections/Questions for Beta Phase (or note 'No Changes') | Tech Lead | Prior to each rollout phase... complete the associated TRA sections. If responses have not changed... note 'no changes'. | ⬜ Pending
BETA | Scoring | Update Risk Scores (based on Alpha findings) | Architect | Enter Technical and Mitigation Risk Scores (+). | ⬜ Pending
BETA | Gate | VAT/Core Review (Required if Scores increased to Med/High) | Zone Architect | Features... set to Medium or High should expect those features to be reviewed by the core technical and product team. | ⬜ Pending
BETA | Signoff | Jira Feature: Engineering Signoff for Beta | Eng Lead | Obtain signoffs within the Jira Feature... required for each phase of release. | ⬜ Pending
BETA | Signoff | Jira Feature: Product Signoff for Beta | Product Owner | Obtain signoffs within the Jira Feature... required for each phase of release. | ⬜ Pending
GA (General Availability) | Assessment | Complete TRA Sections/Questions for GA Phase | Tech Lead | Prior to each rollout phase (Alpha, Beta, GA), complete the associated TRA sections. | ⬜ Pending
GA (General Availability) | Demo | Present in 'Release Preview' (If selected as Top Feature) | Product Owner | Release Preview: teams to showcase the demos of their selected 'top' 3-5 features. | ⬜ Pending
GA (General Availability) | Compliance | Verify GA Date aligns with Tri-Annual Guidance | Release Mgmt | Refer to Tri-Annual Release Guidance page... for dates by which GA signoffs must occur. | ⬜ Pending
GA (General Availability) | Gate (Conditional) | Executive Review (SVP/CPO) - *Only for Off-Cycle External Release* | Eng Leader + PO | Arrange a required approval review with SVP Engineering & Chief Product Officer... and make a final go/no-go decision. | ⬜ Pending
GA (General Availability) | Signoff | Jira Feature: Engineering Signoff for GA | Eng Lead | Obtain GA signoffs within the Jira Feature... A signoff from each of Product and Engineering are required. | ⬜ Pending
GA (General Availability) | Signoff | Jira Feature: Product Signoff for GA | Product Owner | Obtain GA signoffs within the Jira Feature... A signoff from each of Product and Engineering are required. | ⬜ Pending