## tra
Phase | Key Actions Required | Risk & Approval Gates | Outcome / Signoff
1. Planning (Bottom Up Planning - BURP) | • Create TRA in Confluence. • Use TRA questions to define technical approach. • Assign Initial Risk Scores (Technical & Mitigation). | • High Score: Mandatory VAT Lightning Review • Low/Med Score: VAT discretion. | • Initial TRA created. • Risk profile established.
2. Rollout Execution (Prior to Alpha / Beta / GA) | • Update TRA sections for the specific phase • Re-evaluate Scores based on new data/testing. • If a phase is skipped, complete its questions in the next phase. | • High Score: Additional VAT Review required. • Medium Score: Core Technical & Product Team review required. | • Jira Signoffs: Engineering & Product Leads must sign off in the Jira Feature.
3. Standard Release (Tri-Annual GA) | • Complete final TRA updates. • Participate in Release Preview (Demo top 3-5 features). | • Adhere to Tri-Annual Release dates. • Ensure all prior phase signoffs are complete. | • Final GA Signoff in Jira by Product & Engineering.
4. Off-Cycle Release (Internal / Low Sensitivity) | • Full TRA must be complete. • Mitigate any previously identified high risks. | • Engage VAT if high risks remain. | • Final GA Signoff in Jira.
5. Off-Cycle Release (External Facing) | • Notify Release Management immediately. • Submit Revised Assessment (Eng Leader + PO). | • Executive Review: Mandatory Go/No-Go decision by SVP Engineering & CPO, plus VAT. | • Executive Approval. • Final GA Signoff in Jira.

## takeaways
. Risk Classification: MEDIUM
Status: The project has been classified as Medium Risk (downgraded from High).
Condition: This classification is valid only if the "Recursive Scraping" feature is feature-flagged OFF or strictly limited (depth=1) for the initial GA release.
Justification: While the architecture is complex (Hybrid Cloud + AI), it relies on established patterns (CRONs, APIs) and the AI is used for suggestions rather than autonomous financial execution.
2. Critical Architectural Gaps
You must address these four specific technical risks in your implementation stories:
Hybrid Brittleness: The workflow relies on On-Premise CRON jobs triggering AWS ECS Services. This is a known failure point. Mitigation: You must implement retry logic with exponential backoff in the on-prem scripts.
AI Reliability: GPT-4.1 Mini is non-deterministic. Mitigation: A "Golden Dataset" of PDFs must be created to benchmark the model's parsing accuracy in the CI/CD pipeline to detect hallucinations or schema drift.
Legacy Data Integrity: The logic regarding "1 Task = 1 Brid" in the legacy Perl scripts is currently unverified. Action: Confirm this explicitly with the Rules Team before coding to prevent data corruption.
Untested Scalability: Recursive scraping is marked "not fully tested." Action: As noted above, this must be disabled for GA to avoid infinite loops or database flooding.
3. Governance & Process Requirements
To proceed to Alpha/Beta, you must complete the following steps from the TRA Process:
TRA Document: Create the TRA page in Confluence (using the structure we generated).
Review: Schedule a Core Technical Team Review (Tech Lead + Architect). Note: A full VAT Lightning Review is optional for Medium risk but recommended due to the AI components.
Signoffs: Obtain formal signoffs from the Product Owner and Engineering Lead within the Jira Feature's "Signoffs" section.
4. Estimated Effort
Technical Prep: ~12 hours (Diagramming the Hybrid Handoff & AI flows).
Mitigation Prep: ~8 hours (Defining the Golden Dataset & Monitoring dashboards).
Total Documentation Overhead: ~20 hours to be fully audit-ready.