## LLM Council Checklist
Week | Focus | Key Tasks | Deliverables
Week 1 | Foundations | Read LLM Council references; understand multi-model consensus; environment setup | Concept summary + baseline script
Week 2 | Baseline & Orchestration | Single-model baseline; parallel multi-model calls | Council v1 code
Week 3 | Peer Review | Anonymous review; ranking logic; aggregation strategy | Council v2 with rankings
Week 4 | Synthesis | Chairman model; synthesis prompts; output comparison | Council v3 final answers
Week 5 | Evaluation Design | Create evaluation dataset; define metrics | Evaluation plan
Week 6 | Experiments | Run council vs single-model tests; collect metrics | Results tables
Week 7 | Failure Analysis | Identify hallucination, bias, cost failures | Failure analysis doc
Week 8 | Refinement | Prompt tuning; council size experiments | Improved results
Week 9 | Documentation | Architecture diagrams; README polish | Final docs
Week 10 | Final Review | Prepare demo; final recommendation | Final presentation

## RLM Checklist
Week | Focus | Key Tasks | Deliverables
Week 1 | Foundations | Read RLM blog; recursion concepts; environment setup | Concept summary
Week 2 | Baseline | Naive long-context prompting; document failures | Baseline report
Week 3 | Chunking | Document chunking; storage of summaries | Chunked dataset
Week 4 | Recursive Summarization | Recursive summarization depth >1 | RLM v1
Week 5 | Recursive Q&A | Query traversal; refinement logic | RLM v2 answers
Week 6 | Metrics | Token, latency, call-count tracking | Metrics report
Week 7 | Comparison | Compare naive vs recursive results | Comparison table
Week 8 | Failure Analysis | Depth explosion; error propagation cases | Failure analysis
Week 9 | Refinement | Depth control; cost optimizations | Improved RLM
Week 10 | Final Review | Prepare demo; final recommendation | Final presentation