## Docker_PoC
Task | Story Points | Prerequisites | Why Needed / Where Used | Detailed Steps
Setup Docker environment on-prem | 2 | Linux VM/server, admin access | Required to run Langfuse and database locally | Install Docker; verify version; test with hello-world container; ensure network access.
Create Dockerfile for Langfuse | 3 | Langfuse source code or image reference | Build container to deploy Langfuse | Write Dockerfile; include dependencies; define working directory; test image build.
Create docker-compose.yaml for PoC | 2 | Docker installed, Dockerfile ready | Run multiple containers incl. Langfuse and Postgres | Define services; configure ports; include database; run docker-compose up.
Test local deployment | 2 | docker-compose.yaml ready | Validate Langfuse PoC setup | Run docker-compose; check logs; test API endpoint; verify health.
Implement SDK minimal version | 4 | PoC working, SDK structure defined | Enable PHI masking and tracing | Create masking, client wrapper, decorators; write basic unit tests.
Integrate SDK with pilot application | 5 | SDK MVP ready | Test SDK integration | Update imports; add decorators; test LLM calls; validate logs.
Unit tests for masking & tracing | 3 | SDK MVP implemented | Prove PHI safety | Write tests for masking; validate trace output; verify field whitelist.

## K8s_Scale
Task | Story Points | Prerequisites | Why Needed / Where Used | Detailed Steps
Create Kubernetes namespace | 2 | K8s cluster access | Isolate Langfuse in cluster | kubectl create namespace langfuse-poc
Reuse Docker image for K8s | 2 | Docker image built | Same image used across environments | Push image to registry; reference in YAML
Create Deployment YAML for Langfuse | 4 | Docker image available | Run pods in K8s | Write Deployment spec; configure replicas; apply via kubectl
Create Service YAML | 3 | Deployment running | Expose API inside cluster | Define ClusterIP/NodePort; apply via kubectl
Create ConfigMap & Secrets | 4 | K8s cluster ready | Store sensitive config | Use kubectl create secret; mount in deployment
Setup Postgres & ClickHouse in K8s | 5 | Namespace and secrets ready | Langfuse requires DB | Deploy DB pods; assign persistent volumes
Multi-app SDK integration | 6 | SDK stable | Scale to enterprise apps | Test requests; monitor logs; optimize scaling

## Cloud_Future
Task | Story Points | Prerequisites | Why Needed / Where Used | Detailed Steps
Cloud compliance assessment | 4 | Security team inputs | Check HIPAA/BAA needs | Engage compliance; document risks
VPC + Firewall review | 3 | Network architect approval | Secure connectivity | Review outbound rules; test VPN
Cost comparison sheet | 2 | Cloud pricing data | Financial decision making | Collect pricing; compare with on-prem
Legal & compliance discussion | 2 | Compliance assessment ready | Regulatory approval | Risk review; documentation
Cloud K8s prototype YAML | 3 | Cloud account available | Future eval only | Create AKS/EKS spec; test locally