## Docker_PoC
Task | Story Points | Prerequisites | Why Needed / Where Used | Detailed Steps
Setup Docker environment on-prem | 2 | Linux VM/server, admin/sudo access | Foundation to run Langfuse & DB as containers | Install Docker; validate 'docker --version'; test with hello-world container; ensure network access.
Create Dockerfile for Langfuse | 3 | Langfuse source or Docker image reference | Containerize Langfuse for PoC | Write Dockerfile; define dependencies; test build with 'docker build' and local run.
Write docker-compose.yaml | 3 | Dockerfile ready | Run Langfuse + Postgres + ClickHouse | Define services, ports, volumes; test with 'docker-compose up -d'.
Deploy Postgres & ClickHouse | 3 | docker-compose.yaml ready | Langfuse requires DB for tracing | Mount persistent volume; verify health using CLI; create DB user and credentials.
Test full PoC deployment | 2 | Compose up and running | Verify PoC before SDK integration | Test Langfuse UI; check logs; execute example trace call.

## K8s_Scale
Task | Story Points | Prerequisites | Why Needed / Where Used | Detailed Steps
Access Kubernetes cluster | 2 | kubectl installed, cluster access | Required for K8s deployment | Validate access; run 'kubectl get nodes'; check permissions.
Create K8s Namespace | 2 | Cluster connectivity | Isolate Langfuse logically | Run 'kubectl create namespace langfuse-poc'; verify with 'kubectl get ns'.
Push Docker image to registry | 2 | Docker image built | Use same image in K8s | Tag and push image; test registry pull.
Write Deployment.yaml | 4 | Docker image in registry | Deploy Langfuse to K8s | Write deployment spec, env vars, resource limits.
Add Service.yaml | 3 | Deployment active | Expose API inside cluster | Use ClusterIP or NodePort; apply and test connectivity.

## Cloud_Future
Task | Story Points | Prerequisites | Why Needed / Where Used | Detailed Steps
Cloud compliance assessment | 4 | Compliance/legal input | Check HIPAA feasibility | Document data flow; check PHI boundary; review any BAA with vendor.
Firewall + VPC review | 3 | Cloud environment | Ensure secure connections | Check inbound/outbound ports; identity IAM roles.
Cost comparison analysis | 2 | Pricing data | Budget decision | Compare on-prem vs cloud for DB, compute, ingress/egress.

## SDK_Development
Task | Story Points | Prerequisites | Why Needed / Where Used | Detailed Steps
Define SDK folder structure | 2 | Architecture overview confirmed | Developer clarity and modularity | Create directories for masking, tracing, client wrapper, tests.
Implement masking logic | 4 | Regex list for PHI/PII | HIPAA boundary enforcement | Write masking.py; apply regex replacements; validate with unit tests.
Create client wrapper for Azure/OpenAI | 4 | Existing OpenAI usage known | Switch imports to SDK without breaking logic | Design same function signatures; add tracing hooks internally.
Develop decorator for tracing | 3 | PoC deployment working | Track LLM calls | Add @trace decorator; capture duration, model, session ID.
Add unit tests for masking & trace | 3 | masking.py and decorator ready | Prove PHI never leaks | Write pytest cases; validate outbound requests only contain allowed fields.
Sample integration in one application | 5 | SDK MVP ready | Test real integration | Update imports; apply decorators; test fallback mode LANGFUSE_ENABLED=false.
Write developer onboarding doc | 2 | SDK MVP working | KT and developer handoff | Write README.md with install steps and usage examples.