## please put this ina excel sheet
ID | Phase | Task Name | Detailed Action Items | Technical Specifications / Inputs | Owner | Estd. Story Points | Status
LF-01 | Infrastructure | Provision Server | Request and verify EC2 instance provisioning from the Platform Team. | OS: Amazon Linux 2023 Type: t3.xlarge (4 vCPU, 16GB RAM) Disk: 100GB gp3 Net: Private Subnet | DevOps | 0.4 | ⬜ Pending
LF-02 | Setup | SSH Access | Verify connectivity to the instance via Bastion Host or VPN using the private key. | Key: .pem file Command: ssh -i key.pem ec2-user@<ip> | Developer | 0.3 | ⬜ Pending
LF-03 | Setup | Install Docker | Install Docker Engine and enable the service for the ec2-user. | sudo yum install -y docker sudo service docker start sudo usermod -aG docker ec2-user | Developer | 0.4 | ⬜ Pending
LF-04 | Setup | Install Compose | Download and install the Docker Compose v2 plugin binary. | Path: ~/.docker/cli-plugins/ Permission: chmod +x | Developer | 0.4 | ⬜ Pending
LF-05 | Deployment | Create Config | Create the docker-compose.yml file on the server. | Services: langfuse-server, postgres, clickhouse, redis | Developer | 0.4 | ⬜ Pending
LF-06 | Deployment | Launch Stack | Pull images and start the container stack in detached mode. | Command: docker compose up -d Validation: docker compose ps | Developer | 0.4 | ⬜ Pending
LF-07 | Network | Update Firewall | Update AWS Security Group to allow inbound traffic from Corp VPN. | Port: TCP 3000 Source: VPN CIDR Range | DevOps | 0.3 | ⬜ Pending
LF-08 | Config | Init Dashboard | Access Web UI, create Admin account, and generate API Keys. | URL: http://<internal-ip>:3000 Output: Public Key, Secret Key | Developer | 0.4 | ⬜ Pending
LF-09 | Integration | Client Setup | Install Langfuse SDK on local laptop and configure env vars. | Lib: pip install langfuse Vars: LANGFUSE_HOST, PUBLIC_KEY, SECRET_KEY | Developer | 0.5 | ⬜ Pending
LF-10 | Testing | Verify Trace | Run a test Python script to send a dummy trace to the server. | Action: Run script Success Criteria: Trace visible in Dashboard. | Developer | 0.5 | ⬜ Pending