## TRA Form
Technical Readiness Assessment (TRA)
Feature Metadata
Field | Details
Project Name | Policy Loader, Extractor & Analyser Flow
Jira Epic/Feature Link | [Link to Jira]
Target GA Date | [Date]
Tech Lead | @[Name]
Architect | @[Name]
Zone Technical Architect | @[Name]
Product Owner | @[Name]
1. Risk Evaluation Scoring
Risk Category | Score (Low / Medium / High) | Justification / Notes
Technical Risk Score | Medium | • Hybrid Complexity: Mix of AWS ECS services and On-Prem CRONs/Perl scripts. • AI Dependency: Critical logic relies on LLM (GPT-4.1) for parsing and rule updates. • Stability: Recursive scraping is currently 'not tested fully'.
Mitigation Risk Score | [Enter Score] | Evaluate current testing: Do we have automated tests for LLM hallucinations? Do we have monitoring for the On-Prem to AWS handoff?
2A. Assessment: Technical Implementation
Question Area | Key Risks to Address | Alpha Phase Response | Beta Phase Response | GA Phase Response
Service Architecture (Hybrid Handoff) | The Extractor & Analyser run on AWS ECS but are triggered by On-Prem CRONs. Q: What happens if the On-Prem CRON fails to reach the ECS endpoint? Is there a retry mechanism?
Data & Storage (S3 & Postgres) | Storing raw PDFs and Parsed JSONs. Q: Are we adhering to data retention policies for downloaded PDFs? Q: Is the Postgres schema optimized for JSONB queries?
AI/LLM Reliability (GPT-4.1 Mini) | Used for billing scoring and normalization. Q: How do we handle LLM 'hallucinations' or incorrect JSON schemas? Q: Is there human-in-the-loop validation?
Dependencies (Rules Team/Legacy) | Dependence on Perl scripts, 'Birds', and Atlas DB. Q: The Perl script logic ('1 bird = 1 rule') needs verification. Has this been confirmed?
Scalability (Recursive Scraping) | Marked as 'not tested fully'. Q: What prevents the scraper from entering infinite loops or crashing Postgres with massive file counts?
2B. Assessment: Risk Mitigation
Question Area | Mitigation Plan (Specific Qs) | Alpha Phase Response | Beta Phase Response | GA Phase Response
Test Coverage (LLM & Integration) | Q: Do we have a 'Golden Dataset' of PDFs to verify LLM parsing accuracy doesn't degrade? Q: Are there end-to-end tests covering Scraper -> S3 -> ECS -> DB?
Monitoring & Alerts (Observability) | Q: Since parts are On-Prem and parts are AWS, do we have a unified dashboard (e.g., Datadog/Splunk) that traces a job across both?
Performance Tuning (Optimization) | The notes mention 'scope for optimization'. Q: Have we defined latency SLAs for the 24/7 ECS services?
Rollback Plan (Data Corruption) | If the LLM corrupts the 'Rule Impact Summary Table', how do we revert to the previous state?
3. Phase Signoffs
Phase | Engineering Signoff (Name/Date) | Product Signoff (Name/Date) | Status
Alpha |  |  | Pending
Beta |  |  | Pending
General Availability (GA) |  |  | Pending
4. Review Log
Review Type | Date | Reviewers | Outcome
VAT Lightning Review
Security Review (External Scraping)