Policy Watch: Monorepo Migration Estimation Sheet

Project: Policy Watch Monorepo Migration Role: Senior AWS Architect Developer Resource: 2 Developers (Senior Level Assumed) Timeline: 10 Working Days (Strict) Methodology: Agile / Kanban Total Estimated Story Points (SP): ~54 SP (Velocity Target: ~2.7 SP/Dev/Day)

1. Module: Policy Loader (Scraper)

Migration Strategy: Option A (Full ECS Migration) vs Option B (Hybrid Fallback) Architect's Recommendation: Option A is critical for removing on-prem dependency, but carries the IP Reputation risk.

Option A: Cloud Native (Recommended)

- Goal: Move Python scraping logic to packages/tools/policy_retriever.py as an ECS Task.

- Prerequisites: * CRITICAL: Proxy Service (BrightData/SmartProxy) Account & API Key provisioned.

  - Firewall opening for Payer Portals from AWS VPC NAT Gateway.

  - IAM Roles created for S3 (Direct Upload) & Secrets Manager.

| Task ID | Task Description | Dependencies | Story Points | Assignee |
| --- | --- | --- | --- | --- |
| PL-A-01 | Setup Monorepo Scaffold: Create policy_retriever.py in packages/tools/. Implement BaseTool interface. Establish basic logging. | Repo Access | 2 | Dev 1 |
| PL-A-02 | Port Scraping Logic: Migrate existing Python scraper code. Refactor file handling to use Boto3 (Direct S3 Upload), removing "Rule File Service" API calls. | PL-A-01 | 5 | Dev 1 |
| PL-A-03 | Implement Proxy Rotation: Integrate Proxy Service SDK/Config to handle WAF blocking. Configure via Secrets Manager. | Proxy Creds | 3 | Dev 1 |
| PL-A-04 | HTML Scraping Capability: Add BeautifulSoup or Selenium logic for HTML-based policies (New Requirement). | PL-A-02 | 3 | Dev 1 |
| PL-A-05 | ECS Task Def & EventBridge: Create Terraform/CDK for Fargate Task Definition and EventBridge Rule (4h schedule). | IAM Roles | 3 | Dev 2 |
| PL-A-06 | Validation (Shadow Mode): Deploy to Dev. Run in parallel with On-Prem. Compare S3 outputs for parity. | PL-A-02, PL-A-05 | 2 | Dev 2 |

- Total Option A SP: 18

Option B: Hybrid (Fallback)

- Use Case: Execute ONLY if Payer Portals block AWS IPs despite Proxy, or if timeline is at risk on Day 4.

| Task ID | Task Description | Dependencies | Story Points | Assignee |
| --- | --- | --- | --- | --- |
| PL-B-01 | FastAPI Wrapper: Create Python FastAPI wrapper around existing On-Prem script. Expose /scrape endpoint. | On-Prem Access | 3 | Dev 1 |
| PL-B-02 | Monorepo Client: Create policy_retriever.py that simply calls the On-Prem API. | PL-B-01 | 2 | Dev 1 |
| PL-B-03 | Secure Connectivity: Configure Security Groups / VPN routing to allow ECS to talk to On-Prem API. | Network Team | 3 | Dev 2 |

- Total Option B SP: 8

2. Module: Policy Extractor (Parser)

Migration Strategy: Lift & Shift + Optimize (Single Path)

- Goal: Convert 24/7 Service to Event-Driven ECS Task.

- Prerequisites: OpenAI API Key (gpt-4o-mini), S3 Access, SQS Queue created.

| Task ID | Task Description | Dependencies | Story Points | Assignee |
| --- | --- | --- | --- | --- |
| PE-01 | Port to Monorepo: Move code to packages/tools/policy_extractor.py. Implement BaseTool. | None | 3 | Dev 2 |
| PE-02 | Shared DocumentParser: Extract PDF parsing logic to packages/common/document_parser.py. Add HTML parsing support. | None | 3 | Dev 2 |
| PE-03 | SQS Integration (DLQ): Implement logic to read from SQS (triggered by EventBridge). Implement Dead Letter Queue logic for failed parses. | None | 2 | Dev 2 |
| PE-04 | LLM Client Integration: Update model refs to gpt-4o-mini. Use shared LLMClient. | Secrets Mgr | 2 | Dev 2 |
| PE-05 | Infra Setup: Define ECS Task for Extractor. Remove Service auto-scaling configuration. | None | 2 | Dev 1 |

- Total Extractor SP: 12

3. Module: Policy Analyzer (Logic)

Migration Strategy: Port & Orchestrate

- Goal: Move logic to Monorepo. Orchestrate via Step Functions.

- Prerequisites: Rule Ontology Embeddings available in RDS.

| Task ID | Task Description | Dependencies | Story Points | Assignee |
| --- | --- | --- | --- | --- |
| PA-01 | Port Logic: Copy logic to packages/tools/policy_analyzer.py. Verify Top-N matching code against new Monorepo structure. | None | 3 | Dev 1 |
| PA-02 | Step Function Config: Design State Machine JSON. Define WaitForRules state and Parallel execution branches. | None | 3 | Dev 1 |
| PA-03 | Integration Test: Validate Analyzer output against "Golden Set" of policies. | RDS Data | 2 | Dev 1 |

- Total Analyzer SP: 8

4. Module: Rules Loader (Critical Legacy)

Migration Strategy: Option A (Rewrite - Recommended) vs Option B (Wrapper)

- Architect's Note: Option A is high risk for 10 days. If SQL analysis (RL-A-01) reveals high complexity (>100 lines of complex SQL), switch to Option B immediately.

Option A: Python Rewrite (Recommended)

- Goal: Rewrite Perl to Python. Automate via EventBridge.

- Prerequisites: CRITICAL: Site-to-Site VPN or Direct Connect to Oracle (Atlas DB).

| Task ID | Task Description | Dependencies | Story Points | Assignee |
| --- | --- | --- | --- | --- |
| RL-A-01 | Analyze & SQL: Document all SQL queries from Perl script. Validate against Oracle DB connectivity. | Oracle Access | 3 | Dev 2 |
| RL-A-02 | AtlasDBClient: Create packages/connectors/atlas_db.py using cx_Oracle. Implement retry/connection pooling logic. | RL-A-01 | 3 | Dev 2 |
| RL-A-03 | Business Logic Port: Rewrite consolidation logic in packages/rules/rules_loader.py. | RL-A-02 | 5 | Dev 2 |
| RL-A-04 | Shadow Mode: Run ECS task alongside Perl script. Compare JSON output in S3. | RL-A-03 | 2 | Dev 2 |

- Total Option A SP: 13

Option B: Subprocess Wrapper (Interim)

- Goal: Keep Perl, wrap in Python to allow Monorepo orchestration.

| Task ID | Task Description | Dependencies | Story Points | Assignee |
| --- | --- | --- | --- | --- |
| RL-B-01 | Dockerize Perl: Create Dockerfile with Perl runtime + Dependencies. Copy legacy script. | None | 3 | Dev 2 |
| RL-B-02 | Python Wrapper: Create rules_loader.py that uses subprocess.run(['perl', ...]) to invoke script. | RL-B-01 | 2 | Dev 2 |

- Total Option B SP: 5

5. Module: Rules Processor (ML Engine)

Migration Strategy: Event-Driven Automation

- Goal: Trigger on RulesLoadedSuccess.

| Task ID | Task Description | Dependencies | Story Points | Assignee |
| --- | --- | --- | --- | --- |
| RP-01 | Port to Monorepo: Move logic to packages/tools/rules_processor.py. | None | 2 | Dev 1 |
| RP-02 | Event Trigger: Configure BaseTool entrypoint to accept EventBridge payload (RulesLoadedSuccess). | None | 1 | Dev 1 |

- Total Processor SP: 3

6. Execution Timeline (10 Days / 2 Devs)

- Total Recommended SP: 18 (Loader) + 12 (Extractor) + 8 (Analyzer) + 13 (Rules) + 3 (Processor) = 54 SP

- Daily Velocity Requirement: 5.4 SP / Day (Combined). This is an Aggressive schedule.

- Contingency: If RL-A-01 (Perl Analysis) runs over 1 day, Switch Rules Loader to Option B (Saves 8 SP).

| Day | Dev 1 Focus (Loader / Analyzer / Processor) | Dev 2 Focus (Extractor / Rules) |
| --- | --- | --- |
| Day 1 | PL-A-01 (Scaffold), PL-A-02 (Scraper Port - Start) | PE-01 (Extractor Port), PE-02 (DocParser - Start) |
| Day 2 | PL-A-02 (Scraper Port - Finish) | PE-02 (DocParser - Finish), PE-03 (SQS) |
| Day 3 | PL-A-03 (Proxy Integration) | PE-04 (LLM), PE-05 (Infra) |
| Day 4 | PL-A-04 (HTML Support) | RL-A-01 (Perl Analysis) - Decision Point |
| Day 5 | PL-A-05 (Loader Infra), PL-A-06 (Validation) | RL-A-02 (Atlas Client) |
| Day 6 | PA-01 (Analyzer Port) | RL-A-03 (Rules Logic - Start) |
| Day 7 | PA-02 (Step Functions) | RL-A-03 (Rules Logic - Finish) |
| Day 8 | PA-03 (Testing), RP-01 (Processor) | RL-A-04 (Shadow Mode) |
| Day 9 | RP-02 (Events), Integration Testing | Integration Testing (End-to-End) |
| Day 10 | Final Handover / Docs | Final Handover / Docs |