## Sheet1
Priority Level | Action Items | Phase Mapping | Delivery Timeline
Critical | 1. Langfuse infra setup | Phase 1 – Cloud Setup | Before Dec 31
| 2. Instrument GPT-4 calls | Phase 2 – LLM Instrumentation
| 3. Basic error handling | Phase 2 – Error Handling
| 4. Session tracking | Phase 3 – Session ID + Linking
| 5. Cost monitoring | Phase 3 – Cost Tracking
Important | 1. Prompt management migration | Phase 4 – Prompt Store Setup | Try Before Dec 31
| 2. Evaluation datasets | Phase 5 – Golden Dataset
| 3. Real-time dashboards | Phase 6 – Monitoring
| 4. Basic alerting | Phase 6 – Alert Setup
| 5. Data sanitization | Phase 7 – PII/PHI Handling
Enhancement | 1. A/B testing | Phase 10 – Variant Testing | Next Year (2026)
| 2. Advanced evaluators | Phase 10 – Custom Evaluators
| 3. Automated reporting | Phase 9 – Reporting via API
| 4. Performance optimization | Phase 8 – Optimization
| 5. CI/CD integration | Phase 9 – quality-gate pipelines

## Phase 1 Tasks
Phase | Task Group | Task Description | Low-Level Developer Activities | Story Points | Estimated Hours | Assigned To | Status
Phase 1 | Infra Decision | Confirm Langfuse Cloud setup | - Evaluate pricing/tier - Finalize account creation - Create org & project structure proposal | 0.5 | 3
Phase 1 | Cloud Setup | Setup Langfuse organization & projects | - Create org in Langfuse Cloud - Create 3 projects: dev, pre-prod, prod - Record API keys | 1 | 6
Phase 1 | ENV Strategy | Define ENV structure & sampling rules | - Sampling % per env - Trace retention policy - Naming convention for projects - Mandatory metadata tags | 1 | 6
Phase 1 | Secret Storage | Store API keys securely in vault | - Store API keys in AWS SM/Azure KV - Write secret fetch snippet - Add startup validation code | 2 | 12
Phase 1 | ENV Config | Add Langfuse config to existing app template | - Create `.env.example` - Create `langfuse_config.py` - Add fallback `LANGFUSE_ENABLED=false` | 2 | 12
Phase 1 | RBAC Setup | Define roles & assign users | - Map users to roles - Invite users to org - Create access request procedure | 2 | 12
Phase 1 | Trace Tagging Plan | Define tagging convention | - Define mandatory tags: env, payer, model - Create metadata JSON template | 1 | 6
Phase 1 | Runbook | Write Runbook for setup | - How to fetch keys - Troubleshooting access issues - Key rotation procedure | 2 | 12
Phase 1 | Smoke Test | Verify access & API call test | - Test `/projects` API - Check if keys work via REST call - Log healthcheck result | 1 | 6

## Phase 2 Tasks
Phase | Task Group | Task Description | Low-Level Developer Activities | Story Points | Estimated Hours | Assigned To | Status
Phase 2 | LLM Instrumentation | Wrap all Azure GPT-4 calls with Langfuse decorators | - Replace existing OpenAI client with langfuse.openai.AzureOpenAI - Add tracing for chat, completion & embedding calls - Implement `name`, `metadata`, `tags` parameters - Verify token, latency, cost logs captured | 3 | 18
Phase 2 | Embedding Tracing | Trace embedding generation flows | - Identify all embedding calls - Add span tracing using Langfuse SDK - Tag embeddings with policy/doc IDs - Validate cost & latency logging | 2 | 12
Phase 2 | Error Handling | Implement global error handling with fallback | - Add try/except around Langfuse calls - Implement circuit breaker fallback - Ensure pipeline continues on error - Add structured error logs | 3 | 18
Phase 2 | Circuit Breaker | Add circuit breaker pattern for Langfuse API failures | - Implement retry with exponential backoff - Fallback to non-traced execution if Langfuse down - Log circuit breaker activation - Monitor recovery status | 2 | 12
Phase 2 | Langfuse Unavailable Mode | Graceful fallback mode when Langfuse unreachable | - Introduce `LANGFUSE_ENABLED=false` override - Create logging wrapper for fallback - Ensure no pipeline failures in fallback mode - Handle connection timeout & API errors | 2 | 12
Phase 2 | Testing & Validation | Smoke test all LLM instrumentation | - Create sample policy workflow - Validate traces appear in Langfuse UI - Check token tracking - Check error logging - Verify metadata & tags | 2 | 12

## Phase 3 Tasks
Phase | Task Group | Task Description | Low-Level Developer Activities | Story Points | Estimated Hours | Assigned To | Status
Phase 3 | Session Tracking | Implement session tracking for policy workflows | - Generate unique session IDs - Link related operations in same session - Add session metadata (start_time, status, duration) - Implement session recovery logic | 3 | 18
Phase 3 | Session Metadata | Attach metadata across all traces | - Tag sessions with payer, document_type, workflow - Include environment & model metadata - Create JSON metadata template | 2 | 12
Phase 3 | Session Recovery | Resume interrupted pipelines using session ID | - Implement checkpoint mechanism - Store session states - Continue pipeline with previous session ID - Validate session linking in Langfuse UI | 2 | 12
Phase 3 | Cost Tracking | Track cost per LLM operation | - Use token data for pricing - Aggregate cost per workflow - Display daily/weekly/monthly costs - Enable payer/document-type breakdown | 3 | 18
Phase 3 | Cost Alerts | Implement cost threshold alerts | - Add daily & monthly thresholds - Compare costs vs budgets - Create alert triggers to Slack/Teams/email - Log alerts to Langfuse traces | 2 | 12
Phase 3 | Usage Quotas | Set token/budget limits per workflow | - Decide limits per operation type - Implement throttle or fallback when hitting limits - Enable override for critical workflows | 2 | 12
Phase 3 | Automation Reports | Generate automated cost reports | - Create report template - Generate weekly & monthly reports - Integrate via REST API or CRON job - Prepare sample report JSON format | 2 | 12

## Phase 4 Tasks
Phase | Task Group | Task Description | Low-Level Developer Activities | Story Points | Estimated Hours | Assigned To | Status
Phase 4 | Prompt Inventory | Extract all hardcoded prompts from codebase | - Scan codebase for prompt usage - Identify reusable prompt templates - Create inventory list of prompts - Mark prompts with domain/purpose/tag | 2 | 12
Phase 4 | Prompt Migration | Move prompts to Langfuse prompt store | - Upload prompts to Langfuse UI/API - Add variable placeholders ({{payer}}, {{document}}) - Version control each prompt - Add descriptions & metadata | 3 | 18
Phase 4 | Naming Standard | Define naming conventions for prompts | - Create naming schema (e.g., policy_extract_v1) - Decide tags (workflow, model) - Document naming guide - Enforce conventions in migration | 1 | 6
Phase 4 | Prompt Templates | Implement template variable structure | - Identify dynamic fields in prompt - Map variables & fallback values - Create JSON schema for variables - Implement validation logic | 2 | 12
Phase 4 | Prompt Loader | Create code module to load prompts | - Implement `langfuse.get_prompt()` wrapper - Add caching for performance - Add fallback prompt if Langfuse fails - Ensure safe variable substitution | 3 | 18
Phase 4 | Rollback Strategy | Implement prompt version rollback process | - Enable rollback to previous version - Create change approval strategy - Test rollback in staging - Document rollback SOP | 2 | 12
Phase 4 | Prompt Deployment Workflow | Create workflow for prompt promotion | - Create dev > staging > prod flow - Define approval roles (SME, architect) - Add metadata tags (ready_for_prod) - Test promotion in UI/API | 2 | 12
Phase 4 | A/B Testing | Enable prompt-level A/B testing | - Define experiment format - Tag prompts with variant info - Write logic for traffic splitting - Track success metrics per variant | 3 | 18

## Phase 5 Tasks
Phase | Task Group | Task Description | Low-Level Developer Activities | Story Points | Estimated Hours | Assigned To | Status
Phase 5 | Dataset Creation | Create golden dataset (50-100 policy samples) | - Collect real policies (new + updated) - Identify edge cases (FP/FN) - Create structured JSON format - Store in version control | 3 | 18
Phase 5 | Dataset Versioning | Version control datasets and maintain updates | - Tag dataset with schema version - Develop naming convention - Store historical versions safely - Create dataset change log | 2 | 12
Phase 5 | Automated Dataset Validation | Implement dataset validation pipeline | - Ensure JSON schema validation - Validate mandatory fields - Detect duplicates & anomalies - Log invalid samples | 2 | 12
Phase 5 | Evaluation Framework | Build automated evaluation script | - Implement accuracy (TP/FP/FN) metrics - Calculate precision, recall, F1 - Integrate Langfuse traces capturing - Generate summary report | 3 | 18
Phase 5 | Continuous Evaluation | Run evaluations on code/model changes | - Hook evaluation into CI/CD - Trigger evaluation via PR - Fail build on metric regression - Store results in Langfuse history | 3 | 18
Phase 5 | Drift Detection | Detect performance drift over time | - Compare latest vs baseline performance - Track model degradation trends - Create threshold-based alerting - Log drift events in Langfuse | 2 | 12
Phase 5 | Human Feedback Loop | Create manual review interface | - Simple UI for reviewing outputs - Allow SMEs to approve/reject - Track overrides & corrections - Store feedback for retraining | 3 | 18
Phase 5 | Scoring Mechanism | Implement custom scores for domain | - Add custom scoring logic (healthcare rules) - Add evaluator for CPT/modifiers - Track compliance confidence levels - Store scores via Langfuse evaluator API | 3 | 18

## Phase 6 Tasks
Phase | Task Group | Task Description | Low-Level Developer Activities | Story Points | Estimated Hours | Assigned To | Status
Phase 6 | Dashboard Setup | Create real-time monitoring dashboards | - Create dashboards in Langfuse UI - Define dashboard views (Exec/Dev/SRE) - Add metrics: latency, token usage, cost - Enable filtering by payer/workflow | 3 | 18
Phase 6 | Operational Dashboard | Build dashboard for developers | - Show error rate trends - Trace timelines & latency patterns - Track prompt performance - Add trace filtering options | 2 | 12
Phase 6 | Quality Metrics Dashboard | Create dashboard for accuracy & quality tracking | - Show evaluation results (Phase 5) - Track confidence levels - Map trends across payers/doc types - Tag risk zones (underperforming areas) | 3 | 18
Phase 6 | Cost Tracking Dashboard | Build cost tracking view | - Show daily/week/month cost - Break down by model/payer/workflow - Compare cost vs volume - Add cost spikes alert indicators | 2 | 12
Phase 6 | Alerting Setup | Implement alert thresholds & triggers | - Define alert severity levels (INFO/WARN/ERROR) - Implement >5% error alert - Add latency alert (>2x baseline) - Add cost spike alert (>150% avg) | 3 | 18
Phase 6 | Alert Routing | Send alerts to Slack/Teams/Email | - Implement webhook integration - Define routing per severity - Build JSON payload format - Ensure retries for failures | 2 | 12
Phase 6 | Alert Fatigue Prevention | Implement alert deduplication & escalation | - Avoid duplicate alerts - Introduce cooldown period - Provide manual acknowledgment system - Route to PagerDuty only if needed | 2 | 12
Phase 6 | Validation & Smoke Tests | Verify dashboards and alerts | - Trigger simulated errors - Check alert delivery - Validate cost calculations - Confirm trace visibility in dashboards | 2 | 12

## Phase 7 Tasks
Phase | Task Group | Task Description | Low-Level Developer Activities | Story Points | Estimated Hours | Assigned To | Status
Phase 7 | PII Detection | Implement PII identification & masking | - Define PII regex rules - Create sanitization middleware - Mask before sending to Langfuse - Log masked/unmasked version for audit | 3 | 18
Phase 7 | Data Classification | Add data classification tags to traces | - Define classification levels: internal, confidential, PHI - Add metadata tags to traces - Validate tags in Langfuse UI - Document tagging policy | 2 | 12
Phase 7 | Audit Logging | Create audit log system for trace access | - Log user access to sensitive traces - Store audit logs securely - Integrate with Langfuse APIs - Provide access review reports | 2 | 12
Phase 7 | Retention Policy | Implement trace retention & auto-purging | - Define retention periods per environment - Configure auto-delete scripts - Tag traces with expiry date - Test data deletion process | 3 | 18
Phase 7 | Data Export | Enable compliance-driven data export | - Create trace export script/API - Define JSON/CSV format - Restrict access to export API - Build compliance logging | 2 | 12
Phase 7 | Right-to-Deletion | Implement GDPR delete request flow | - Add `delete_trace_by_user()` API - Validate user ownership - Create compliance approval flow - Log deletion for audit | 3 | 18
Phase 7 | Access Control | Enforce role-based trace visibility | - Define roles (HIPAA safe roles) - Restrict PHI visibility for general users - Add read-only & masked view modes - Test access matrix across roles | 3 | 18
Phase 7 | Compliance Runbook | Create compliance & HIPAA guidance doc | - Document redaction flows - Provide access request SOP - Describe retention policies - Include compliance guidelines for devs | 2 | 12

## Phase 8 Tasks
Phase | Task Group | Task Description | Low-Level Developer Activities | Story Points | Estimated Hours | Assigned To | Status
Phase 8 | Intelligent Sampling | Implement adaptive sampling for traces | - Sample 100% for errors & edge cases - Sample 10-20% for successful requests - Add dynamic sampling based on load - Provide config in env variables | 3 | 18
Phase 8 | Trace Compression | Optimize trace data size before logging | - Trim large prompts/results - Compress long text fields - Avoid unnecessary metadata - Enable structured logging | 2 | 12
Phase 8 | Async Submission | Enable non-blocking trace submission | - Convert to async trace sending - Add retry + queue mechanism - Prevent blocking API calls - Log timeout occurrences | 3 | 18
Phase 8 | Batch Upload | Batch traces to improve performance | - Enable batching buffer - Flush traces per interval - Use batch size threshold - Monitor memory usage | 2 | 12
Phase 8 | Local Buffering | Store traces locally during network failure | - Save traces to local file/Redis temporarily - Retry sending after recovery - Test network failure scenarios - Track dropped vs processed traces | 3 | 18
Phase 8 | Cache Optimization | Optimize prompt caching strategy | - Implement Redis/in-memory caching layer - Add TTL per cache entry - Ensure cache invalidation logic - Monitor cache hit/miss ratio | 3 | 18
Phase 8 | Connection Pooling | Implement connection pooling for Langfuse | - Configure max connections limit - Enable keep-alive for persistent sessions - Monitor connection failures - Prevent socket exhaustion | 2 | 12
Phase 8 | Load Testing | Benchmark tracing performance under load | - Run load tests with locust/k6 - Track CPU/memory usage - Measure latency added by Langfuse - Provide load test report | 2 | 12

## Phase 9 Tasks
Phase | Task Group | Task Description | Low-Level Developer Activities | Story Points | Estimated Hours | Assigned To | Status
Phase 9 | CI/CD Integration | Integrate Langfuse into CI/CD pipeline | - Add evaluation script to CI/CD - Block deployment on regression - Fetch metrics via Langfuse API - Add version tracking in trace metadata | 3 | 18
Phase 9 | Deployment Validation | Trace deployments & compare performance | - Create deployment trace - Capture latency & cost - Store model version & git commit - Detect regression automatically | 2 | 12
Phase 9 | Automated Regression Checks | Fail builds if quality drops | - Compare with baseline model - Set min accuracy thresholds - Add F1/latency/cost checks - Send failure report | 3 | 18
Phase 9 | Slack/Email Notifications | Notify on build pass/fail | - Integrate webhook/API alerts - Send detailed deployment report - Format JSON payload - Include metrics summary | 2 | 12
Phase 9 | Automated Reporting | Generate weekly & monthly Langfuse reports | - Fetch data via Langfuse API - Generate PDFs/JSON - Schedule via cron/lambda - Store reports in S3 or Confluence | 3 | 18
Phase 9 | Runbook & Incident Handling | Create operational runbooks | - Document issue resolution - Trace failure steps - Create incident playbook - Link traces to support tickets | 2 | 12
Phase 9 | API Integration | Expose Langfuse data via REST endpoints | - Create API wrapper layer - Allow dashboard to consume metrics - Expose evaluation & cost data - Secure end-points with auth | 3 | 18

## Phase 10 Tasks
Phase | Task Group | Task Description | Low-Level Developer Activities | Story Points | Estimated Hours | Assigned To | Status
Phase 10 | A/B Testing | Implement framework for prompt/model experimentation | - Define experiment schema - Implement variant assignment logic - Track metrics per variant - Use Langfuse metadata for trace tagging | 3 | 18
Phase 10 | Prompt Variant Analysis | Compare prompt versions | - Create metric aggregation script - Define statistical comparison rules - Track precision/recall/F1 per prompt variant - Store results in Langfuse | 2 | 12
Phase 10 | Model Comparison | Evaluate GPT-4 vs GPT-3.5 for workflow | - Run A/B tests between models - Track latency/cost/quality - Provide recommendation algorithm - Create model-switch config | 3 | 18
Phase 10 | Evaluator Framework | Build custom evaluators (Healthcare-specific) | - Implement CPT/modifier validator - Validate payer-specific rules - Track rule compliance via Langfuse scores - Add chained evaluations | 3 | 18
Phase 10 | Continuous Learning | Create production feedback loops | - Identify successful traces - Feed outputs into dataset - Track human overrides - Label production data for retraining | 3 | 18
Phase 10 | Improvement Suggestions | Suggest prompt/model improvements using data | - Aggregate failure patterns - Generate Langfuse insights - Recommend prompt edits - Flag low-confidence outputs | 2 | 12
Phase 10 | Domain Accuracy Check | Implement billing/healthcare rule consistency checks | - Define consistency metrics - Compare similar policy outputs - Implement taxonomy-based evaluator - Use Langfuse evaluator API | 3 | 18